## Sheet1
No. | Project | Description | List of all API | Status (Dev/UAT/Live/REQ) | Start date (dev) | Go live Date | BUSINESS FPR | BUSINESS HEAD | Team Lead | Remark | Developer
1 | VideoKYC - UNFYD | Credit Card Personal Loan Travel Card 3in1 Unified Journey | Encr Decr 1.customer handshake 2.callwait time 3.videokyc status 4.kycdownload 5. Kyc regularisation | UAT |  | Live |  | Bijith Bhaskar | Priyanshu | Parag P Handover | Arvind Bukya
2 | eSign | eSign via NSDL | Store PDF | Dev | Monday, November 23, 2020 | Saturday, November 28, 2020 |  | Ravi Narayanan | Priyanshu | Parag P Handover | Arvind Bukya
3 | Bahrain Tokenization | Bahrain Govt project to allow tokenization of ICICI Bank VISA debit cards | Encr Decr | UAT | Thursday, October 15, 2020 | Tuesday, November 24, 2020 |  | Vikash Sharma | Priyanshu | Parag P Handover | Arvind Bukya
4 | Prepaid Cards | PCMS API changes for complaince | Card Topup | REQ | Tuesday, November 24, 2020 | TBD |  | NIraj Tralshwala | Priyanshu | Parag P Handover | Venkat / Ankit
5 | Travel Card | Insta FX Corporate Solution | TBD | REQ | Monday, November 16, 2020 | TBD | Ravi Kiran |  | Priyanshu |  | Venkat
|  | Travel Card NLI | Travel card application from NLI | DEV | Thursday, November 26, 2020 | Wednesday, December 09, 2020 | Ravi Kiran |  | Priyanshu |  | Venkat
6 | Stand Alone FD | Direct FD creation services for external clients for both NTB and ETB using eazypay and UPI | TBD | REQ | TBD | TBD | Priti Kulkarni |  | Priyanshu |  | Naveen
7 | 3in1 Uinfied Journey | Service to push and pull data in DWH | TBD | REQ | TBD | TBD | Bhaskar Srivastava |  | Priyanshu |  | Himanshu/Vikash